Akkodis, Inc.

4800 Deerwood Campus Parkway, Building 800, Jacksonville, FL 32246,

United States of America

Akkodis Response for

UNT Health

University of Texas

Table of Contents

Cover Letter:	4

1. Executive Summary	5

2. Our Understanding of the Client’s Objectives	6

2.1 Business Objectives	6

2.2 Scope of Work (SOW)	7

2.3 Technical Requirements	8

2.4 Out of Scope	8

3. Proposed Technical Solution & Architecture	9

3.1 Solution Overview	9

3.2 Architecture Explanation	10

3.3 End-to-End System Flow	11

3.5 DevSecOps & CI/CD Automation	12

3.6 Benefits of the Proposed Architecture	12

3.7 Security & Compliance Architecture (TX-RAMP Alignment)	13

5. Agile / Hybrid Agile Methodology & Sprint Governance	19

5.2 Sprint Setup & Execution	19

5.3 Core Agile Ceremonies	20

5.5 Benefits of Agile	21

6. Delivery Frameworks (DevSecOps, Agile Engineering Practices & Platform Accelerators)	22

6.1 DevSecOps & CI/CD Framework	22

7. Work Breakdown Structure (WBS)	27

8. Testing & Quality Engineering Approach	28

8.1 Test Types and Execution Flow	28

8.2 Test Cycle Activities Overview	28

8.3 Defect Management & Governance	29

8.4 Roles in Testing Cycles	30

8.5 Security Testing (SAST & DAST)	30

8.6 Test Environments (Reusable Standard Set)	30

9. Risk Management & Mitigation Strategies	32

9.1 Key Risk Areas & Mitigation Strategies	32

9.2 Risk Governance	32

9.3 Continuous Improvement Through Agile Practices	32

10. Rollout & Go-Live Strategy	33

10.1 Progressive Rollout Model (Alpha → Beta → Production)	33

10.2 Deployment Readiness & Cutover Planning	34

10.3 Deployment Execution	34

10.4 Production Verification & Smoke Testing	35

10.5 Post-Go-Live Hypercare & Stabilization	35

10.6 Transition to Steady-State Operations	35

11. Assumptions and Dependencies	35

11.1 Assumptions	35

11.2 Dependencies	36

12.  Pricing Summary	38

13.  Case Studies:	39

# Cover Letter:

July 7, 2025

UNT Health

RE: Opportunity for providing the response for UNT Health

Dear  XXXXX,

Thank you for providing Akkodis with the opportunity to provide a response to the Clients Request to Provide strategic technology and business services specific to the UNT Health.

Brief Summary of Partnership with the Client.

Empowered by a culture of inclusion and diversity, our 50,000 tech experts across 30 countries combine best-in-class technologies and cross industry knowledge to drive purposeful innovation for a more sustainable tomorrow. Our pioneering approach empowers businesses to explore, innovate and accelerate new possibilities, while creating a dynamic culture for our people. 

Our Services and Solutions:

- Talent Services – we provide our clients with flexible and scalable talent services. We draw on our large local and national candidate networks to identify, recruit, and fast track the onboarding of the right talent to fill flexible or permanent roles within client organizations, enabling them to be more agile and flexible.

- Consulting Services – we provide our clients with highly skilled project-specific expertise, supporting them in scaling capacity, accelerating innovation, and improving time to market.

- Solutions Services – we provide end-to-end solutions – from ideation to realization – to our clients. We capitalize on our cross-sectoral technology, engineering, and digital expertise to deliver specific project outputs and outcomes preestablished by the client.

- Academy Services – we provide training and certification services to our clients. We train new talents for clients or upskill/reskill their existing teams, enabling them to futureproof their talent and drive performance.

Based on our history of service to the Client and our industry leading expertise in providing information technology staff augmentation services to public sector clients, it is our sincere hope that the client will select Akkodis as its partner in delivering exceptional service. 
 
Should you have any questions, please contact me directly. 
 
Sincerely, 

Name

Designation

E:  xxxxxx@akkodisgroup.com

T:  (xxx) xxx-xxxx  

Engineering a Smarter Future Together https://www.Akkodis.com/en-us/

# 1. Executive Summary

University of North Texas Health / UNT System is seeking a technology partner to design, build, and support a modern digital platform that enables mentorship programs, professional networking, community engagement, and conference and event management within a unified environment. The objective of this initiative is to create a secure, scalable, and accessible platform that supports collaboration between students, mentors, professionals, reviewers, and administrators while enabling efficient program management and event participation.

Akkodis proposes to design and develop a modern, cloud-aligned digital platform that integrates mentorship workflows, community interaction, event and conference management, and abstract submission and review processes into a single solution. The platform will be built using modern web technologies and an API-driven architecture, enabling seamless integration with enterprise systems such as identity providers, communication platforms, and learning systems. The proposed solution will prioritize security, scalability, accessibility (WCAG 2.1 AA), and compliance with TX-RAMP aligned cloud security practices.

To accelerate implementation while maintaining flexibility and compliance, Akkodis will adopt a modular architecture approach. Where appropriate, open-source frameworks or proven components may be leveraged to support capabilities such as event management or community interaction, provided they are deployed within the client-approved infrastructure and meet the client’s security, governance, and TX-RAMP compliance requirements. This approach enables faster delivery while maintaining full control of platform data and infrastructure.

The platform will be delivered using an Agile implementation model with a dedicated cross-functional delivery team. The project will follow structured two-week sprint cycles with regular demonstrations, stakeholder feedback, and iterative feature delivery. This model ensures continuous alignment with business needs while enabling incremental delivery of platform capabilities. The Akkodis delivery team will include business analysts, solution architects, UX designers, full-stack developers, integration engineers, quality assurance specialists, and DevOps engineers working collaboratively throughout the development lifecycle.

The proposed platform will deliver:

• Modern, responsive user interfaces for mentors, mentees, reviewers, administrators, and event participants
• Configurable mentorship, event, and abstract review workflows to streamline program management
• Secure API-based integrations with identity providers, communication tools, and learning platforms
• A scalable backend architecture capable of supporting growing user communities and increasing event participation
• Administrative dashboards and analytics to track mentorship engagement, platform usage, and event participation
• Secure cloud-based infrastructure aligned with TX-RAMP security and compliance practices

By partnering with Akkodis, UNT System gains access to a global team of experienced platform engineers, cloud architects, and DevSecOps specialists with deep expertise in secure enterprise application development. Our delivery methodology, combined with automated testing, modern DevOps practices, and scalable architecture design, ensures predictable timelines, reduced implementation risk, and measurable business value.

This initiative will provide UNT System with a modern digital platform that strengthens mentorship programs, enables efficient conference and event management, and fosters professional collaboration across the community. The solution establishes a strong foundation for long-term innovation, scalability, and digital transformation.

# 2. Our Understanding of the Client’s Objectives

This section summarizes Akkodis’ understanding of the client’s goals for implementing a modern digital platform that enables mentorship programs, professional networking, community engagement, and conference/event management within a unified environment. The initiative focuses on creating a scalable, secure, and accessible platform that supports collaboration among students, professionals, mentors, administrators, and event participants while aligning with the organization’s technology and compliance standards.

## 2.1 Business Objectives

The primary objective of this engagement is to design, architect, and implement a modern digital platform that supports mentorship programs, networking communities, and conference/event management within a secure and scalable environment.

Key business objectives include:

1. Deliver a modern and intuitive user experience

- Provide a clean, responsive user interface accessible across web and mobile device.

- Enable easy navigation for mentors, mentees, reviewers, presenters, and administrators.

- Simplify user interactions and reduce onboarding complexity

2. Enable collaboration and knowledge sharing

- Provide a centralized platform where users can connect, communicate, and share knowledge.

- Support community discussions, resource sharing, and professional networking.

- Facilitate mentorship relationships between mentors and mentees

3. Support event and conference management

- Enable event creation, registration, and participant engagement

- Provide agenda management and session scheduling capabilities

- Support abstract submission, reviewer assignment, and evaluation workflows

4. Build a scalable and future-ready digital platform

- Implement a modular and extensible platform architecture

- Support integration with enterprise systems such as identity providers and communication tools

- Ensure the system can scale as user participation and event volumes grow

5. Ensure security, compliance, and accessibility

- Implement strong authentication and role-based access control

- Ensure accessibility compliance aligned with WCAG 2.1 AA standards

- Design infrastructure and services aligned with TX-RAMP cloud security requirements

6. Provide insights through reporting and analytics

- Enable dashboards and reporting capabilities for administrators

- Track mentorship engagement, event participation, and community activity

- Support data-driven decision making for program management

## 2.2 Scope of Work (SOW)

The scope of this initiative includes the design and development of a new digital platform with the required functional, technical, and operational capabilities.

- Business & Functional Discovery

- Conduct workshops with stakeholders to define platform requirements

- Identify user roles such as mentors, mentees, reviewers, presenters, and administrators

- Define workflows for mentorship programs, events, and abstract review processes

- Create product backlog including epics, features, and user stories

- Experience Design & Prototyping

- Develop UX/UI wireframes and interactive prototypes

- Ensure alignment with client branding and usability expectations

- Design accessible user interfaces compliant with WCAG guidelines

- Platform Architecture & Application Development

- Design scalable platform architecture with modular components

- Develop user management, mentorship workflows, event management, and community modules

- Implement configurable business workflows and validation rules

- Develop reusable components and shared service libraries

- API & Integration Services

- Implement API-first architecture for system integrations

- Integrate with identity providers for SSO authentication

- Support integration with communication tools and learning platforms

- Enable future integrations using secure REST APIs

- Data Architecture & Database Development

- Design data models supporting users, mentorship sessions, events, submissions, and analytics

- Implement secure cloud database infrastructure

- Enable reporting and analytics for platform activity and engagement

- DevSecOps, Automation & Cloud Enablement

- Establish CI/CD pipelines for automated build and deployment

- Implement Infrastructure-as-Code for environment provisioning

- Perform automated security scanning and vulnerability checks

- Deploy platform on a TX-RAMP compliant cloud environment

- Quality Engineering & Testing

- Develop comprehensive testing strategy and test cases

- Perform functional, integration, performance, and security testing

- Conduct accessibility validation and automated regression testing

- Deployment, Go-Live & Hypercare

- Prepare and deploy application plan – alpha, beta releases

- Deploy application in production environment

- Provide post-go-live stabilization and hypercare support (30 days)

- Transfer knowledge and documentation to the client team

## 2.3 Technical Requirements

The following technical elements are critical for delivering a secure and scalable platform.

- Application Layer Requirements

- Develop responsive web interfaces using modern UI frameworks

- Implement backend services supporting mentorship workflows, event management, and community features

- Provide role-based dashboards for different user personas

- Ensure modular and extensible application architecture

- Integration Layer Requirements

- Implement API-based integrations with enterprise systems

- Integrate with identity providers for secure authentication

- Enable event-driven integrations and secure data exchange

- Implement standardized authentication and encryption mechanisms

- Data Layer Requirements

- Design secure data storage for users, events, mentorship activities, and submissions

- Enable analytics and reporting for administrators

- Implement audit logs and activity tracking for compliance

- Security & Compliance Requirements

- Implement secure authentication through SSO and identity providers

- Apply role-based access controls and data protection policies

- Ensure encryption of data in transit and at rest

- Maintain compliance with TX-RAMP security standards and institutional policies

## 2.4 Out of Scope

The following activities are considered outside the scope of the initial implementation unless formally agreed through change control:

- Migration of legacy systems or external platforms not identified in the scope

- Full institutional brand redesign or development of enterprise design systems

- Development of additional products or modules unrelated to mentorship, community, or event management

- Long-term operational support beyond the agreed hypercare period

- Procurement or licensing costs for third-party software or external services

- Management of end-user devices or internal network infrastructure

# 3. Proposed Technical Solution & Architecture

## 3.1 Solution Overview

The proposed solution will deliver a secure, scalable digital platform that enables mentorship programs, professional networking, community collaboration, and conference/event management within a unified environment.

The platform will support multiple user roles including students, mentors, reviewers, presenters, administrators, and program managers, allowing them to interact through a single digital ecosystem.

The solution will be designed using a modular architecture with modern web technologies, enabling flexible expansion of platform capabilities and seamless integration with external services such as identity providers, communication tools, and learning platforms.

The platform will be hosted on a cloud infrastructure aligned with TX-RAMP security practices, ensuring secure data handling, compliance, and scalability for growing user communities and event participation.

Below is the target architecture supporting these capabilities.

Discourse -> Community forums

Pretalx -> Event Scheduling

Pretalx CFP -> Abstract Submission

SendGrid/Twilio -> Communication

Platform DataStore

UserProfiles, Events, Mentorship, Submissions

Analytics & Reporting

Platform Engagement, Mentorship, Event Participation Metrics

Identity Provider

SSO / OAuth

Integration Services

Webinar Platforms / LTI Systems/ SSO/ VideoTools/ Calendar

DevSecOps Pipeline

CI/CD, Security Scans, Monitoring, Logging

Web & Mobile UI

React Web/ Responsive Interface

USERS & FRONT-END

API Gateway/ BFF

Authentication / Routing / RBAC

HTTPS/ REST API’s

API GATEWAY & SECURITY

HTTPS / REST API’s

APPLICATION SERVICE

LAYERS

PLATFORM COMPONENTS

DATA & INTEGRATION

EXTERNAL

INTEGRATIONS

PIPELINE

## 3.2 Architecture Explanation

The architecture follows a layered modular design that separates presentation, application services, and data management.

- Presentation Layer

The presentation layer provides responsive user interfaces accessible through web and mobile browsers. This layer delivers role-based dashboards for mentors, mentees, reviewers, presenters, and administrators, enabling easy access to platform capabilities.

B. Application Services Layer

This layer contains the core platform capabilities including:

- Mentorship management and matching workflows

- Community forums and collaboration features

- Event and conference management

- Abstract submission and review workflows

- Communication and notification services

These services are implemented as modular application components that communicate through secure APIs.

C. Data & Integration Layer

The data layer stores platform data such as user profiles, mentorship activities, event details, submissions, and analytics information.

Integration services enable connectivity with:

- Identity providers for secure authentication

- Video conferencing and communication platforms

- Learning platforms and external partner systems

All integrations follow secure API-based communication patterns.

3.2.1 Platform Components and Open-Source Accelerators

To accelerate delivery while maintaining flexibility and compliance, Akkodis may leverage selected open-source or SaaS-based platform components for specific capabilities of the solution. These components will be deployed within the client-approved infrastructure and evaluated to ensure alignment with institutional security policies and TX-RAMP compliance expectations.

Potential platform components include:

Community Collaboration Platform

To support community discussions, knowledge sharing, and professional networking, the platform may integrate a community discussion engine such as Discourse, which provides scalable forum capabilities including threaded discussions, moderation tools, notifications, and user engagement features.

Conference & Event Management

For conference and event workflows, Akkodis may leverage components such as Pretalx, an open-source conference management platform that supports event scheduling, session management, and participant coordination.

Abstract Submission & Call for Papers

The abstract submission and review workflows may utilize capabilities similar to Pretalx CFP (Call for Papers) to support:

- abstract submission by presenters

- reviewer assignment

- scoring and evaluation workflows

- acceptance and rejection processes

Communication & Notification Services

The platform will support automated notifications and communication services using enterprise messaging platforms such as:

- SendGrid for email notifications and platform communications

- Twilio for SMS notifications or multi-channel messaging where required

These services support automated notifications for mentorship sessions, event updates, submission status changes, and administrative communications.

All third-party services will undergo security validation and deployment approval in accordance with institutional governance policies and TX-RAMP security practices.

## 3.3 End-to-End System Flow

The system flow describes how users interact with the platform and how components communicate across layers.

- Users access the platform through a responsive web interface.

- Authentication is handled through a secure identity provider using SSO.

- The application layer processes requests related to mentorship, events, community interactions, and abstract submissions.

- Data is stored in a secure cloud database designed for platform scalability.

- Integration services connect the platform to external systems such as communication tools and learning platforms.

- Administrative dashboards provide real-time visibility into platform activity, mentorship engagement, and event participation.

This flow ensures efficient user interaction while maintaining secure and scalable system operations.

3.4 Smart Mentor–Mentee Matching Implementation

The platform will include a smart mentor–mentee matching capability designed to connect participants based on shared interests, goals, expertise, and availability. The matching functionality will evolve in stages to ensure both reliability and flexibility while maintaining full administrative oversight.

Phase 1 – Rule-Based Matching with Administrative Controls

During the initial implementation, the platform will provide an intelligent rule-based matching engine combined with administrative control features. This ensures that mentorship relationships can be recommended automatically while allowing program administrators to manage and adjust matches as needed.

The matching engine will analyze profile attributes such as:

- professional interests and areas of expertise

- career goals and mentorship objectives

- industry or academic discipline

- geographic location or time zone

- availability and preferred mentoring format

- experience level

Each attribute will be assigned configurable matching weights, allowing administrators to define how recommendations are calculated.

Example scoring model:

| Matching Attribute | Example Weight |
| --- | --- |
| Area of expertise | 30% |
| Career goals alignment | 25% |
| Experience level | 20% |
| Location / timezone | 15% |
| Availability | 10% |

The platform will calculate a matching score and recommend the most suitable mentor–mentee pairs.

Administrative Controls

Administrative users will have full visibility and control over the mentorship matching process. Key capabilities will include:

- configuring matching criteria and scoring weights

- reviewing system-generated mentor recommendations

- manually assigning mentor–mentee pairs when needed

- approving or overriding automated matches

- monitoring mentorship engagement and activity

These controls ensure program managers can maintain oversight and adjust matching behavior based on program objectives.

## 3.5 DevSecOps & CI/CD Automation

Akkodis will implement a DevSecOps-enabled delivery pipeline to ensure secure, reliable, and automated platform deployment.

Key practices include:

- Continuous integration pipelines for automated code builds and testing

- Automated security scans and vulnerability assessments

- Infrastructure-as-Code for consistent environment provisioning

- Automated deployment pipelines for Dev, Test, and Production environments

- Centralized monitoring, logging, and performance tracking

This approach improves development velocity while ensuring system reliability and security compliance.

## 3.6 Benefits of the Proposed Architecture

The proposed architecture delivers several advantages aligned with the client’s objectives.

Scalability
The modular architecture supports growth in user participation, event activity, and platform capabilities.

Security & Compliance
The solution incorporates strong authentication, role-based access control, and cloud infrastructure aligned with TX-RAMP security practices.

Flexibility & Extensibility
The architecture enables future enhancements such as new mentorship programs, additional event capabilities, or integration with external systems.

Operational Efficiency
Automated workflows and integrated services reduce manual processes and improve administrative efficiency.

Faster Innovation
The modular architecture and DevSecOps automation allow rapid introduction of new features while maintaining system stability.

## 3.7 Security & Compliance Architecture (TX-RAMP Alignment)

The proposed platform will be designed with a security-first architecture aligned with the Texas Risk and Authorization Management Program (TX-RAMP) requirements and industry best practices. Akkodis will implement layered security controls across identity management, application security, data protection, infrastructure security, and monitoring to ensure the platform protects sensitive user data and complies with institutional governance standards.

The architecture incorporates defense-in-depth security principles, ensuring that security controls are implemented at multiple levels of the platform.

1. Identity & Access Management

The platform will implement secure identity management using enterprise authentication mechanisms.

Key capabilities include:

- Integration with institutional Single Sign-On (SSO) systems

- Support for OAuth2 / OpenID Connect authentication standards

- Role-Based Access Control (RBAC) to manage permissions for different user roles such as mentors, mentees, reviewers, administrators, and event participants

- Multi-factor authentication support where required

- Session management and secure token-based authentication

These mechanisms ensure that only authorized users can access platform resources.

2. Data Protection & Encryption

All sensitive data will be protected using strong encryption and secure storage practices.

Security measures include:

- Encryption in transit using TLS 1.2 or higher

- Encryption at rest using cloud provider encryption services

- Secure handling of personally identifiable information (PII)

- Database access restrictions and credential management

- Tokenization or masking of sensitive fields where required

These measures ensure that data remains protected both during transmission and while stored in the system.

3. Application Security

The application will follow secure development practices aligned with DevSecOps principles.

Key controls include:

- Secure coding standards and code review processes

- Automated static application security testing (SAST)

- Dynamic application security testing (DAST) during testing stages

- Dependency vulnerability scanning

Protection against common vulnerabilities such as:

- SQL injection

- cross-site scripting (XSS)

- cross-site request forgery (CSRF)

These practices ensure vulnerabilities are detected early and addressed before deployment.

4. Infrastructure & Cloud Security

The platform will be deployed within a TX-RAMP aligned cloud environment using secure infrastructure configurations.

Infrastructure security controls include:

- Network segmentation and firewall protection

- Secure cloud identity and access management

- Infrastructure-as-Code for controlled environment provisioning

- Secrets management through secure vault services

- Container or application environment hardening

These controls ensure the infrastructure environment meets the security expectations required for public sector cloud systems.

5. Logging, Monitoring & Threat Detection

Continuous monitoring will be implemented to detect anomalies and maintain system integrity.

Key monitoring capabilities include:

- Centralized logging for application and infrastructure activities

- Real-time monitoring of system health and performance

- Security event monitoring and alerting

- Integration with security information and event management (SIEM) tools

- Audit logs for all critical administrative actions

These capabilities help identify suspicious activity and support incident response processes.

6. Compliance & Governance

The platform architecture will be aligned with TX-RAMP security control frameworks, ensuring that the solution adheres to the required compliance standards for cloud systems used by Texas state agencies and public institutions.

Compliance measures include:

- Alignment with NIST 800-53 security control principles, which underpin TX-RAMP requirements

- Implementation of data governance and retention policies

- Audit readiness through structured logging and reporting

- Vendor and third-party security review for external services

- Secure configuration and vulnerability management practices

These governance mechanisms ensure the platform can pass institutional security assessments and maintain compliance throughout its lifecycle.

7. Secure DevSecOps Pipeline

Security will be embedded throughout the development lifecycle through a DevSecOps pipeline.

Key capabilities include:

- Automated security scans during code commits

- Container and dependency vulnerability scanning

- Secure artifact repositories

- Infrastructure security validation before deployment

- Continuous compliance checks within CI/CD pipelines

This ensures that security is integrated from development through deployment and operations.

8. Benefits of the Security Architecture

The proposed security and compliance framework provides:

- Strong protection of user data and institutional information

- Alignment with TX-RAMP cloud security standards

- Reduced risk of security vulnerabilities and breaches

- Continuous monitoring and audit readiness

- A secure foundation that supports future platform expansion

The platform will be designed to align with TX-RAMP security expectations and cloud governance practices, enabling the solution to operate within secure environments used by Texas public institutions.

4. Delivery & Execution Approach (Phased Approach)

Akkodis proposes a 28-week Agile delivery model to design, develop, test, and deploy the digital platform that supports mentorship programs, networking communities, event management, and abstract review workflows. The delivery model is structured into six implementation phases, ensuring a controlled progression from requirements discovery through production deployment and post-go-live stabilization. The implementation approach emphasizes iterative delivery, strong stakeholder collaboration, and secure cloud deployment aligned with TX-RAMP security expectations.

The project will be delivered by a dedicated cross-functional Agile team consisting of business analysts, architects, UX designers, developers, integration engineers, QA specialists, and DevOps engineers. Development will follow two-week sprint cycles, allowing incremental feature delivery, continuous testing, and regular stakeholder demonstrations.

Phase 1 – Discovery & Requirements

Duration: Weeks 1–4

This phase focuses on understanding business requirements and defining the functional scope of the platform.

Key Activities

• Conduct stakeholder workshops and requirement discovery sessions
• Identify platform user roles such as mentors, mentees, reviewers, presenters, and administrators
• Define mentorship workflows and program structures
• Define event management and abstract submission workflows
• Identify integration requirements including SSO, video conferencing, LTI systems, and calendar integrations
• Finalize MVP scope and implementation roadmap

Phase 2 – Solution Design & Platform Architecture

Duration: Weeks 3–10

This phase defines the technical architecture and prepares the platform foundation for development.

Key Activities

• Create UI/UX wireframes and user journey designs
• Define platform architecture across front-end, services, data, and integration layers
• Design database schema for platform entities such as users, mentorship sessions, events, and submissions
• Define API design and integration patterns
• Establish security architecture including authentication, RBAC, and compliance considerations
• Provision development and testing environments
• Configure DevOps pipelines and CI/CD automation

Phase 3 – Core Platform Development

Duration: Weeks 7–20

This phase involves iterative development of the core platform capabilities using Agile sprints.

Key Activities

• Develop user account management and role-based dashboards
• Implement mentorship matching and session management capabilities
• Build messaging, scheduling, and calendar integration features
• Develop community engagement modules including forums and announcements
• Implement event registration and agenda management functionality
• Build abstract submission and review workflows
• Develop administrative dashboards and reporting capabilities
• Implement notification and communication services

Regular sprint reviews and demonstrations will be conducted with stakeholders to validate functionality and gather feedback.

Phase 4 – Testing & Validation

Duration: Weeks 21–23

This phase ensures the platform meets quality, security, and accessibility requirements before production deployment.

Key Activities

• Perform system integration testing across platform modules
• Conduct accessibility validation aligned with WCAG 2.1 AA standards
• Execute security testing and compliance validation
• Conduct user acceptance testing with key stakeholders
• Perform performance testing for event registration and user activity scenarios

Phase 5 – Deployment & Go-Live

Duration: Week 24

This phase prepares the platform for production deployment and operational readiness.

Key Activities

• Execute production deployment through CI/CD pipelines
• Validate production environment configuration
• Perform post-deployment smoke testing
• Confirm system stability and readiness for end users

Phase 6 – Hypercare Support

Duration: Weeks 25–28

Following production launch, Akkodis will provide stabilization and operational support.

Key Activities

• Provide user onboarding and training sessions
• Deliver platform documentation and operational runbooks
• Conduct knowledge transfer sessions for client IT teams
• Monitor application performance and system health
• Provide hypercare support and issue resolution

Implementation Timeline Summary

| Phase | Duration | Key Focus |
| --- | --- | --- |
| Phase 1 | Weeks 1–4 | Discovery and requirements definition |
| Phase 2 | Weeks 5–10 | Architecture design and environment setup |
| Phase 3 | Weeks 11–20 | Core platform development |
| Phase 4 | Weeks 21–23 | Testing and validation |
| Phase 5 | Weeks 24 | Deployment and go-live |
| Phase 6 | Weeks 25–28 | Hypercare and knowledge transfer |

# 5. Agile Methodology & Sprint Governance

Akkodis applies a Agile delivery methodology tailored for digital platform development, enabling rapid iteration, continuous validation, and predictable delivery outcomes. Because the proposed solution involves building a new platform that integrates mentorship workflows, community collaboration, event management, and abstract review capabilities, Agile provides the flexibility required to progressively refine requirements and validate functionality with stakeholders.

Our approach combines Scrum-based sprint execution with structured governance, ensuring delivery speed while maintaining strong quality, security, and compliance controls aligned with TX-RAMP security expectations.

5.1 Agile Delivery Model

The Agile delivery model supports iterative development of the platform’s core components, including user management, mentorship workflows, event management, and community collaboration features.

Key characteristics of our Agile model include:

- Early establishment of platform architecture, design system, and reusable UI components

- Incremental development of platform modules such as mentorship management, event management, abstract review workflows, and community engagement capabilities

- Continuous integration and automated testing integrated from the early development stages

- Regular sprint demonstrations to validate user interfaces, workflows, and integrations with stakeholders

- Early focus on non-functional requirements such as security, scalability, accessibility, and performance

This approach ensures that the platform is developed in a structured, flexible, and user-driven manner, allowing continuous feedback and improvement.

## 5.2 Sprint Setup & Execution

Akkodis uses two-week sprint cycles to support iterative platform development and continuous stakeholder engagement. Each sprint produces a tested and demonstrable increment of the platform.

Sprint Setup

• Sprint length: 2 weeks
• Initial Sprint (Sprint 0):

- Platform architecture validation

- Development environment setup

- DevSecOps pipeline configuration

- UI design system initialization

Parallel Development Workstreams

During development sprints, the team works across multiple workstreams including:

• UI/UX design and responsive interface development
• Platform services development for mentorship, community, and events
• API and integration services
• Security and identity management integration
• Automated testing and quality assurance

Sprint Activities

Backlog Refinement
Ongoing refinement of Epics → Features → User Stories aligned with platform capabilities.

Development
Implementation of UI components, backend services, API integrations, and platform modules.

Testing
Execution of unit testing, integration testing, and automated regression testing within the sprint.

Sprint Demo / Review
Demonstration of completed platform functionality to stakeholders.

Sprint Retrospective
Evaluation of sprint performance, team collaboration, and improvement opportunities.

Each sprint produces deliverables that can be validated in development or staging environments.

## 5.3 Core Agile Ceremonies

Sprint Planning

Define sprint goals aligned to business priorities

Select User Stories based on story points and team velocity

Confirm acceptance criteria, dependencies, and environment readiness

Daily Scrum

15-minute team sync on progress, blockers, and priorities

Facilitated by the Scrum Master to maintain transparency and momentum

Backlog Grooming (Refinement)

Held once or twice per sprint

Prioritize new requirements, clarify acceptance criteria, and size stories

Ensure readiness of features for upcoming sprint planning

Sprint Review

Demonstrate completed sprint work to Product Owner and stakeholders

Validate UI/UX, business logic, API responses, and integrations

Capture feedback for the next sprint

Sprint Retrospective

Analyze what went well, what needs improvement, and action items

Enhance collaboration, throughput, and delivery discipline\

5.4 Governance & Reporting Framework

Agile execution is supported by a structured governance model that ensures transparency, stakeholder engagement, and proactive risk management.

Tools & Platforms

- Jira / Azure Boards for backlog management and sprint tracking

- Azure DevOps / GitHub Actions / GitLab CI for CI/CD automation

- Confluence / SharePoint for documentation management

- Power BI dashboards for project analytics and reporting

Weekly Governance & Reporting

- Weekly status reports covering progress, achievements, risks, and upcoming milestones

- Continuous tracking of risks and issues through RAID logs

- Sprint health dashboards showing velocity, completion rates, and defect trends

- Quality dashboards covering test coverage, automation metrics, and security scan results

Steering Committee Oversight

Periodic steering committee meetings ensure executive visibility and alignment.

Participants typically include:

- Client leadership stakeholders

- Akkodis delivery leadership

- Program and project managers

Key topics discussed include:

- milestone progress and delivery updates

- risk mitigation strategies

- scope alignment and change management

- key architectural or program decisions

## 5.5 Benefits of Agile

The Agile methodology provides several benefits for this platform implementation:

- Requirements can evolve progressively based on stakeholder feedback

- User interface and user experience designs improve through iterative validation

- Core platform components such as authentication, APIs, and integrations can be built incrementally

- Frequent sprint demonstrations build stakeholder confidence and ensure alignment

- Early detection of functional or performance issues reduces delivery risk

- Continuous integration and automated testing improve product quality

- The final platform aligns closely with the client’s operational and user expectations

# 6. Delivery Frameworks (DevSecOps, Agile Engineering Practices & Platform Accelerators)

Akkodis applies a modern engineering delivery framework that integrates DevSecOps automation, Agile delivery practices, and standardized engineering accelerators to deliver secure and scalable digital platforms efficiently. This framework ensures predictable execution, consistent quality, and continuous improvement throughout the lifecycle of the project.

The delivery approach leverages a dedicated cross-functional team structure, where architects, developers, QA engineers, and DevOps specialists collaborate closely throughout the development lifecycle. Automation, standardized engineering practices, and integrated security controls ensure reliable platform delivery aligned with TX-RAMP security expectations.

## 6.1 DevSecOps & CI/CD Framework

The proposed solution will be developed, tested, deployed, and monitored through a fully integrated DevSecOps pipeline, ensuring that security, quality, and deployment automation are embedded from the beginning of the project.

A. Source Control & Branching Strategy

The platform source code will be managed through centralized repositories using tools such as Azure Repos, GitHub, or GitLab.

A structured branching strategy will be used:

- Main / Master branch – Production-ready code

- Develop branch – Integration branch for active sprint work

- Feature branches – Individual development work for user stories

- Release branches – Stabilization before production deployment

Pull request policies will enforce:

- mandatory peer code reviews

- automated build validation

- quality gate checks before merge

B. Automated Build, Testing & Quality Gates

Automated build pipelines will ensure code quality and early defect detection.

Key capabilities include:

- Automated compilation of front-end and backend components

- Static code analysis using tools such as SonarQube or CodeQL

- Automated execution of unit tests with defined code coverage thresholds

- Dependency vulnerability scanning

- Artifact packaging and versioning through repository management tools

These practices ensure code quality and consistency across development cycles.

C. Continuous Deployment Pipeline

Automated CI/CD pipelines will support consistent deployment across environments.

Typical environment flow includes:

Development → System Integration Testing → UAT → Production

Deployment automation will include:

- Infrastructure provisioning using Infrastructure-as-Code (IaC) tools such as Terraform or Bicep

- Automated application deployment pipelines

- Configuration management to maintain environment consistency

- Automated database schema updates where applicable

This approach minimizes manual deployment errors and supports repeatable releases.

D. DevSecOps Security Controls

Security is embedded throughout the development and deployment lifecycle.

Security controls include:

- Static Application Security Testing (SAST) during code builds

- Dynamic Application Security Testing (DAST) during testing phases

- Secure secrets management using vault-based solutions

- Secure API authentication using OAuth2 or OpenID Connect

- TLS encryption for all service communications

These controls support alignment with TX-RAMP security and compliance requirements.

E. Monitoring, Logging & Observability

Operational monitoring ensures system stability and performance visibility.

Monitoring tools may include:

- Application performance monitoring tools such as Application Insights or Datadog

- API latency and response monitoring

- Centralized log aggregation for troubleshooting and audit purposes

- Automated alerts for system failures, performance issues, or unusual activity

These capabilities enable proactive issue detection and rapid response.

6.2 Agile Delivery Team Structure

Akkodis will deploy a single integrated Agile delivery team composed of cross-functional roles that collaborate throughout the project lifecycle.

The delivery team includes:

- Business Analysts for requirement analysis and stakeholder coordination

- Solution Architect for platform architecture and technical governance

- UX Designer for user interface design and usability optimization

- Full-stack Developers for application development

- Integration Engineer for API development and external integrations

- QA Engineers for testing and validation

- DevOps Engineer for CI/CD automation and environment management

- Scrum Master and Project Manager for Agile facilitation and delivery governance

This team structure ensures:

- close collaboration across roles

- rapid feedback loops during sprint execution

- consistent ownership of platform development

6.3 Engineering Accelerators & Best Practices

To improve development efficiency and maintain high engineering standards, Akkodis applies a set of proven engineering accelerators and best practices. These accelerators help reduce development effort, improve maintainability, and accelerate delivery timelines.

A. Reusable Platform Components

Reusable components and selected platform accelerators will be leveraged to accelerate feature delivery and reduce implementation complexity. Where appropriate, Akkodis may utilize proven open-source components such as Discourse for community collaboration capabilities and Pretalx / Pretalx CFP for conference management and abstract submission workflows, as described in Section 3.2.1 Platform Components and Open-Source Accelerators.

Additional reusable components developed within the platform may include:

- user authentication and role management modules

- notification and messaging frameworks (integrating services such as SendGrid for email notifications and Twilio for SMS messaging)

- reusable UI components and design system libraries

- API service templates and standardized response models

These reusable assets reduce development effort and improve maintainability while enabling faster feature development.

- Automated Testing Frameworks

Automated testing frameworks help maintain platform quality throughout development.

Capabilities include:

- automated regression testing for critical platform features

- API testing frameworks for integration validation

- test data management and reusable test scripts

- integration of test automation into CI pipelines

- Development Standards & Code Quality

Standardized development practices will be implemented across the project.

These include:

- coding standards and architectural guidelines

- peer code review processes

- centralized documentation for APIs and services

- version control and change management practices

Outcome of the Delivery Framework

The proposed delivery framework provides:

- secure and automated software delivery processes

- consistent engineering standards and code quality

- improved deployment reliability and faster release cycles

- strong alignment with TX-RAMP security expectations

- efficient collaboration within a cross-functional Agile team

This framework enables Akkodis to deliver the platform efficiently, securely, and with high development quality.

6.4 Optional AI-Assisted Engineering Accelerators (Future Consideration)

As part of Akkodis’ engineering practices, we continuously evaluate the use of AI-assisted engineering accelerators that can enhance development productivity, improve quality assurance, and support faster delivery cycles. While the proposed implementation will primarily rely on established engineering practices, DevSecOps automation, and standardized development frameworks, Akkodis may explore opportunities to leverage AI-assisted tools during later phases of the project, subject to client approval and alignment with institutional security policies and TX-RAMP compliance requirements.

The introduction of AI-enabled development accelerators would only be considered after the platform architecture, security framework, and operational constraints are fully validated. Any such tools would undergo appropriate security and governance review before adoption.

Potential areas where AI-assisted engineering capabilities may be applied include:

AI-Assisted Development Productivity

AI-enabled tools can help accelerate routine engineering tasks such as:

- generating boilerplate code for APIs, service layers, and data models

- suggesting reusable components based on existing platform patterns

- assisting developers in maintaining coding standards and best practices

These capabilities help reduce repetitive coding tasks and allow engineers to focus on core platform functionality.

AI-Enhanced Testing & Quality Engineering

AI-assisted testing tools can improve testing coverage and reduce manual effort through:

- automated test case generation based on user stories and acceptance criteria

- intelligent regression test creation for UI workflows and APIs

- automated defect classification and root cause pattern analysis

These capabilities help improve test coverage and accelerate validation cycles.

Intelligent Impact Analysis

AI tools can assist development teams by identifying potential system impacts when introducing new features or changes. This includes:

- identifying dependent modules and APIs that may be affected

- highlighting potential integration risks before deployment

- supporting faster validation of platform updates

This improves change management and reduces the risk of unintended regressions.

Automated Documentation Support

AI-assisted documentation tools can help generate and maintain technical documentation such as:

- API documentation and interface descriptions

- architecture diagrams and component relationships

- technical design documentation

This ensures documentation remains current throughout the development lifecycle.

AI-Enhanced Mentor–Mentee Matching (Future Enhancement – Phase 2 – After Initial Build of Phase 1)

As the platform matures and mentorship interaction data becomes available, the matching engine may also be enhanced with AI-assisted recommendation capabilities to improve mentor–mentee matching accuracy.

AI-assisted matching capabilities may include:

- learning from successful mentor–mentee pairings

- analyzing feedback ratings and mentorship engagement levels

- recommending mentors based on behavioral patterns, expertise, and user interests

These insights can help generate more personalized mentor recommendations over time while improving the overall effectiveness of mentorship programs.

Any AI-enabled matching capabilities would be introduced only after review and approval of the client’s security, governance, and compliance policies, ensuring alignment with institutional standards and TX-RAMP requirements.

Governance & Security Alignment

Any AI-assisted engineering tools considered for the project would be evaluated to ensure compliance with the client’s security, governance, and regulatory requirements, including alignment with TX-RAMP cloud security standards where applicable.

Akkodis will work closely with the client’s technology and security teams to determine whether selected AI-enabled development tools can be safely introduced to enhance engineering productivity without compromising security or compliance obligations.

Outcome

By selectively introducing AI-assisted engineering capabilities at appropriate stages of the project, Akkodis can potentially:

- reduce repetitive development effort

- improve testing coverage and quality assurance

- accelerate delivery of platform enhancements

- enhance documentation and knowledge sharing

- improve mentor–mentee matching accuracy over time

These capabilities will be considered as optional accelerators, implemented only when aligned with client requirements and security policies.

# 7. Work Breakdown Structure (WBS)

Resource Structure

# 8. Testing & Quality Engineering Approach

Akkodis follows a multi-layered, shift-left testing approach to ensure that quality, security, performance, and usability are validated continuously throughout the platform development lifecycle. Testing activities begin early in the development process and continue across all environments using a combination of manual testing, automated validation, performance testing, and security testing.

This approach ensures that the digital platform supporting mentorship programs, community engagement, event management, and abstract review workflows is validated at every stage of development and is ready for secure production deployment.

Testing activities are integrated into the Agile delivery model, with validation occurring during each sprint and continuing through system integration and user acceptance testing phases.

## 8.1 Test Types and Execution Flow

Platform solutions require validation across multiple layers including user interfaces, APIs, platform workflows, data integrity, integrations, and security controls.

Testing progresses from individual components to full end-to-end platform validation.

| Phase | Test Type | Description | Responsibility |
| --- | --- | --- | --- |
| Build Phase | Unit Testing | Validate individual functions, API endpoints, and business logic at component level | Developer |
|  | Integration Testing | Validate interaction between UI, APIs, services, and database components | Developer + QA |
| Quality Phase | System Integration Testing (SIT) | Validate platform workflows such as mentorship sessions, event registration, and abstract submission processes | QA |
|  | User Acceptance Testing (UAT) | Validate real-world user scenarios with business stakeholders | Client (Vendor Support) |
| Non-Functional | Security Testing | Identify vulnerabilities through static and dynamic security testing | DevSecOps Team |
|  | Accessibility Testing | Validate compliance with WCAG 2.1 AA accessibility requirements | QA |

## 8.2 Test Cycle Activities Overview

Testing activities are integrated within Agile sprint cycles and progressively validate system maturity.

Unit Testing

• Validate platform services, business logic, and API endpoints
• Ensure code coverage thresholds and proper exception handling
• Execute automatically through CI pipelines during code commits

Integration Testing

• Validate interaction across platform modules such as:

- user authentication and role management

- mentorship workflows

- event registration processes

- abstract submission and review workflows

- messaging and notifications

• Validate data exchange between application services and database
• Use mock services where external integrations are unavailable

System Integration Testing (SIT)

• Validate complete end-to-end workflows across platform modules
• Verify business rules, workflow logic, and validation rules
• Validate integration with identity providers and external services
• Verify logging, error handling, and recovery scenarios

Accessibility Testing

Because the platform must meet WCAG 2.1 AA accessibility standards, the testing process includes:

• keyboard navigation validation
• screen reader compatibility checks
• color contrast and usability verification
• accessible form controls and navigation structures

User Acceptance Testing (UAT)

UAT validates that the platform meets business expectations and operational needs.

Activities include:

• validation of mentorship program workflows
• validation of event and conference management features
• role-based access validation
• confirmation of functional acceptance criteria

The client team typically leads UAT execution with vendor support.

## 8.3 Defect Management & Governance

Defect management is integrated into the Agile delivery workflow using standard DevOps tools.

Tools

- Azure DevOps / Jira – defect tracking and sprint management

- CI/CD pipelines – automated build and validation

- documentation platforms – technical documentation and issue tracking

Defect Lifecycle

- QA team logs the defect with detailed information.

- Product owner reviews and prioritizes the issue.

- Developer fixes the defect and submits a code update.

- CI pipeline triggers automated validation and build.

- QA team retests the defect and confirms resolution.

Key metrics tracked include:

- defect density

- defect resolution time

- test coverage

- regression stability

## 8.4 Roles in Testing Cycles

| Role | Client Responsibility | Akkodis Responsibility |
| --- | --- | --- |
| Business SMEs | Execute business test scenarios | Support UAT preparation and validation |
| Developers | Implement fixes and unit testing | Support integration testing |
| QA Engineer | Internal validation | Test planning, SIT execution, automation |
| DevOps Engineer | Environment stability | CI/CD automation and pipeline integration |

## 8.5 Security Testing (SAST & DAST)

Security validation is embedded throughout the development lifecycle to support secure platform operations aligned with TX-RAMP security expectations.

Static Application Security Testing (SAST)

- Conducted during the build pipeline

- Identifies insecure code patterns and dependency vulnerabilities

Dynamic Application Security Testing (DAST)

- Executed in integration or staging environments

- Identifies runtime vulnerabilities and misconfigurations

Role-Based Access Validation

- Validate role-based access controls for all user personas

- Ensure correct permissions for mentors, mentees, reviewers, and administrators

## 8.6 Test Environments (Reusable Standard Set)

The platform will be validated across multiple controlled environments to ensure stability prior to production release.

| Environment | Purpose |
| --- | --- |
| Development | Initial developer testing and integration |
| Test / QA | Internal functional and regression testing |
| SIT | Full system integration testing |
| UAT | Client-led acceptance testing |
| Pre-Production | Final deployment validation |
| Production | Live platform environment |

Outcome of the Testing Strategy

This structured testing approach ensures:

- early detection of defects and security vulnerabilities

- continuous validation of platform functionality

- compliance with accessibility and security requirements

- high confidence in production readiness

The result is a stable, secure, and scalable platform that meets both functional and non-functional requirements.

# 9. Risk Management & Mitigation Strategies

## 9.1 Key Risk Areas & Mitigation Strategies

| Risk Area | Description | Mitigation Strategy |
| --- | --- | --- |
| Requirement Ambiguity | Business requirements may evolve during development | Conduct structured discovery workshops and validate requirements during sprint reviews |
| Integration Dependencies | Delays in external system integrations (SSO, video platforms, LTI) | Use mock services and early integration validation during development |
| Environment Readiness | Delays in environment setup may impact development timeline | Coordinate environment provisioning during early project phases |
| Security & Compliance | Security validation may introduce additional implementation steps | Align platform architecture with institutional security policies and perform early security reviews |
| User Adoption | Users may require time to adapt to the new platform | Introduce Alpha and Beta rollout phases for early user feedback |
| Change Management | Scope changes during development may affect delivery schedule | Implement structured change control and backlog prioritization |

## 9.2 Risk Governance

Risk governance is integrated into the overall project management framework.

Governance Activities

- Maintain a centralized RAID log tracking all risks and mitigation plans

- Review risks during weekly delivery status meetings

- Escalate high-priority risks to project leadership when necessary

- Monitor mitigation effectiveness and update risk status regularly

## 9.3 Continuous Improvement Through Agile Practices

The Agile delivery model supports proactive risk management by enabling:

- early validation of functionality through sprint demonstrations

- rapid identification of issues during development cycles

- continuous improvement through sprint retrospectives

- progressive validation through Alpha and Beta platform releases

This iterative approach significantly reduces implementation risks compared to traditional delivery models.

Outcome

Through structured risk management practices, Akkodis ensures that potential challenges are proactively addressed and that the platform implementation remains aligned with project objectives, timelines, and quality expectations. This approach supports the successful delivery of a secure, scalable, and user-friendly platform that meets the client’s functional and operational goals.

# 10. Rollout & Go-Live Strategy

The rollout strategy for the proposed platform follows a progressive release approach, incorporating Alpha and Beta launch phases before the final production release. This staged rollout ensures that platform functionality, usability, performance, and integrations are validated in controlled environments prior to full deployment.

The approach enables early feedback from stakeholders and pilot users while minimizing operational risk during the final launch.

Alpha Launch

- Internal Validation

- Core Modules Testing

- Admin Users & SMEs

Platform Development

- Limited Pilot Users

- Mentorship Workflows

- Event & Abstract Flow

- User Feedback Cycle

Beta Launch

Production

Launch

- Full user Onboarding

- Platform wide Access

- Monitoring & Support

Hypercare

Support

- Stabilization Period

- Rapid Issue Response

- Performance Tuning

## 10.1 Progressive Rollout Model (Alpha → Beta → Production)

The platform will be deployed using a phased release model that introduces functionality gradually through controlled platform releases.

The rollout stages include:

Alpha Release

The Alpha release is deployed to an internal group of administrators and program managers to validate core platform capabilities including mentorship workflows, community interaction, event registration, and abstract submission features.

Objectives of the Alpha stage include:

• validating platform functionality
• verifying integration with identity providers
• testing core workflows and administrative controls
• identifying early usability feedback

Beta Release

The Beta release expands platform access to a limited set of real users such as mentors, mentees, reviewers, and event participants.

Objectives include:

• validating real user workflows
• collecting usability feedback
• testing platform scalability and performance
• refining platform features prior to final release

Production Release

Following successful Beta validation, the platform will be promoted to full production availability.

This progressive rollout ensures:

• reduced deployment risk
• early feedback cycles
• improved usability and stability before large-scale adoption

## 10.2 Deployment Readiness & Cutover Planning

Prior to production deployment, Akkodis will conduct a Go-Live Readiness Review to ensure that all deployment prerequisites are satisfied.

Deployment Readiness Checklist

| Readiness Item | Owner |
| --- | --- |
| Production infrastructure validated | DevOps Team |
| CI/CD pipelines approved for production | DevOps Team |
| All Alpha and Beta feedback addressed | Delivery Team |
| Security configuration and RBAC validated | Architect + Delivery Team |
| Monitoring and logging enabled | DevOps Team |
| Documentation and user guides prepared | Delivery Team |
| Hypercare support team ready | Delivery Team |

The Go / No-Go decision will be jointly confirmed by client stakeholders and Akkodis delivery leadership.

## 10.3 Deployment Execution

The platform will be deployed using automated CI/CD pipelines, ensuring consistency and reliability across environments.

Deployment Activities

- automated deployment to the production environment

- configuration of secure environment variables and monitoring services

- validation of identity provider integration and system connectivity

Deployment will be coordinated through a centralized rollout coordination process, ensuring that any issues are quickly identified and addressed.

## 10.4 Production Verification & Smoke Testing

Following deployment, Akkodis will conduct a structured smoke testing process to validate system functionality.

Smoke Testing Activities

- verify authentication and user login processes

- validate role-based dashboards and permissions

- test mentorship workflow creation and session scheduling

- validate event registration and agenda functionality

- confirm abstract submission and review workflows

- verify system notifications and integrations

The platform will be declared live only after successful completion of these validation checks.

## 10.5 Post-Go-Live Hypercare & Stabilization

Following the production launch, Akkodis will provide a hypercare support period to ensure system stability and rapid issue resolution.

Hypercare Activities

- continuous monitoring of system health and performance

- rapid triage and resolution of user-reported issues

- monitoring of platform usage and adoption trends

- support for administrators and early platform users

## 10.6 Transition to Steady-State Operations

After the hypercare period, the platform will transition to steady-state operations.

Transition Activities

- knowledge transfer sessions for client IT teams

- handover of documentation, deployment pipelines, and operational runbooks

- confirmation of monitoring and support processes

- preparation of backlog items for future platform enhancements

Outcome

This staged rollout strategy ensures:

- early validation of platform functionality through Alpha testing

- real user feedback through Beta pilot deployment

- a stable and well-validated production release

- reduced deployment risk and improved user adoption

# 11. Assumptions and Dependencies

## 11.1 Assumptions

The following assumptions apply to the implementation of the proposed digital platform unless otherwise agreed with the client.

Access & Environment Assumptions

- The client will provide access to the required cloud environments and infrastructure necessary to host the platform.

- Development, testing, and production environments will be provisioned and made available according to the project timeline.

- Required networking configurations, security policies, and access approvals will be completed in time to support development and testing activities.

Identity & Authentication Integration

- The client will provide access to the institutional identity provider to enable secure authentication and Single Sign-On (SSO).

- User provisioning and identity governance policies will be managed by the client’s identity and security teams.

- The platform will integrate with the client’s approved authentication mechanisms and security standards.

Stakeholder & SME Participation

Business stakeholders, program administrators, and technical representatives will be available for:

- requirements workshops and design validation

- sprint reviews and demonstrations

- user acceptance testing and sign-off

- feedback during Alpha and Beta platform releases

Timely feedback and decision-making will be provided to maintain the planned delivery schedule.

Functional & Technical Scope

- Core platform functionality such as mentorship workflows, community collaboration, event management, and abstract submission/review processes will be defined during the discovery and design phases.

- Any new requirements identified after design approval will follow a formal change management process.

Accessibility & Compliance

- The platform will be designed to meet WCAG 2.1 AA accessibility standards, and the client will provide branding guidelines or accessibility expectations where applicable.

- The platform will align with institutional security and compliance policies including TX-RAMP security expectations for cloud-hosted systems.

Licensing & Tooling

- Access to required development and collaboration tools (e.g., project tracking, documentation platforms, or DevOps pipelines) will be provided by the client or mutually agreed upon at project initiation.

- Any third-party software licenses or external platform services required for integrations will be reviewed and approved by the client prior to implementation.

Project Timeline & Coordination

- The implementation timeline assumes timely availability of environments, integration information, and stakeholder feedback.

- Any delays related to environment setup, access approvals, or integration dependencies may impact the project schedule.

## 11.2 Dependencies

Successful implementation of the platform depends on several client-side inputs and collaboration points.

Infrastructure & Environment Readiness

- Availability of development, testing, staging, and production environments.

- Configuration of networking, firewall policies, and security settings required for platform deployment.

- Access to monitoring and logging infrastructure required for system observability.

Messaging & Notification Services

- The platform may leverage messaging services such as SendGrid for email notifications and Twilio for SMS-based notifications. Access to these services and associated API credentials will be required for integration and testing.

Integration & External Systems

The platform may require integration with external services such as:

- institutional identity providers for authentication

- video conferencing platforms for mentorship sessions or virtual events

- learning systems supporting LTI integration

- messaging or notification services

Timely availability of integration documentation, API specifications, and authentication details will be required.

Data & Configuration Inputs

- Initial configuration data such as user roles, event categories, program structures, and system configuration settings will be provided by the client.

- Reference data and configuration inputs required for platform setup will be available during the development phase.

Stakeholder Collaboration

Business SMEs and administrators will participate in:

- validation of mentorship workflows

- review of community and event management features

- user acceptance testing during the Beta release stage

Client IT teams will support environment readiness, identity management, and infrastructure configuration.

Security & Governance Dependencies

- The client will provide institutional security policies, governance standards, and compliance requirements relevant to the platform.

- Security validation activities such as vulnerability scans or penetration testing will be coordinated with the client’s security teams according to the agreed timeline.

# 12.  Pricing Summary

The total fees for Services provided by the Company shall be as follows:

Time & Materials Fees and Invoicing. Client shall pay Company for the Services in this requirement on an hourly basis at the hourly rates listed below.  The total fees for labor expenses associated with the hours for each resource are also estimated as below –

| Role / Skillset | Location | Bill Rate / Hourly Fee | Estimated Duration (Number of hours) | Estimated Total Labor Expenses |
| --- | --- | --- | --- | --- |
| Business Analysts | U.S. |  | 800 |  |
| Project Manager | India |  | 1120 |  |
| Scrum Master | India |  | 800 |  |
| Solution Architect | India |  | 480 |  |
| Senior Full stack Developer | India |  | 1120 |  |
| Junior Full stack Developer | India |  | 960 |  |
| Devops Engineer | India |  | 480 |  |
| UX Designer | India |  | 480 |  |
| Integration/ Dev Engineer | India |  | 640 |  |
| QA Engineer (Manual) | India |  | 960 |  |
| Estimated Total Labor Fee |  |  |  |  |

- In addition to the above, out of pocket expenses and pre-approved travel expenses will be billed on actuals.

- For the provided roles, the Company will invoice the Client on a monthly basis based on the actual hours worked by the resources and the hourly rates provided.

- Client and Company may enter into a Change Request for any change in the scope of work which requires an addition or removal of the resources. The Agreement provisions will apply for any additional resources.

- Any required hardware/software costs will be billed at actuals via monthly subscription or cost like Desktop.

Milestone Payment Schedule Summary – REMOVE IF NOT NEEDED

| Item No. | Description | Cost |
| --- | --- | --- |
| 1 | Completion of Detailed Design Phase |  |
| 2 | Completion of Build & Unit Testing Phase |  |
| 3 | Completion of SIT & UAT |  |
| 4 | Go-Live and Hypercare Completion |  |
| Total Deliverables: |  |  |

Maximum Budget (Services and Deliverables)	$

# 13.  Case Studies: